## S-MRP UAT Script
System: M2OSS S-MRP
Objective: To verify that the S-MRP Dashboard correctly: Displays shortage risk data, Supports site selection (PHO/THO),Executes Shortage Predictor worker, Displays Digital Worker activities, Allows PR/RFQ action completion.
Test | Objective | Business Condition | Steps | Expected Result | Actual Results | Status: [Pass/Fail] | Notes | Tester Name | Date Executed
UAT-SMRP-001 Dashboard Load | Verify S-MRP dashboard loads successfully. |  | 1. Navigate to S-MRP Dashboard. 2. Observe page loading. | • Dashboard loads without error. • "MOSS S-MRP Decision Cockpit" title displays. • Live Shortage Risk card displays. • Shortage Risk Analysis table displays. • Digital Worker Activity Log displays.
UAT-SMRP-002 Site Selection | Verify site switching functionality. |  | 1. Open dashboard. 2. Select PHO. 3. Verify page refreshes. 4. Select THO. 5. Verify page refreshes. | • Dashboard reloads. • URL contains: ?site=PHO OR: ?site=THO • Shortage data changes according to selected site.
UAT-SMRP-003 Manual Refresh | Verify Refresh button reloads dashboard. |  | 1. Click Refresh button. | • Refresh icon spins. • Button text changes to: • Refreshing... • Dashboard reloads after refresh.
UAT-SMRP-004 Shortage Risk Summary | Verify shortage summary card displays data correctly. |  | 1. Load dashboard. | Card displays: • Material Count • Critical Count • High Count
UAT-SMRP-005 Shortage Filter - Critical | Verify Critical filter. |  | 1. On Shortage Risk Analysis table, click Critical filter. | Only Critical-risk records appear.
UAT-SRMP-006 Shortage Filter - High | Verify High filter. |  | 1. On Shortage Risk Analysis table, click High filter. | Only High-risk records appear.
UAT-SMRP-007 Shortage Filter - Medium | Verify Medium filter. |  | 1. On Shortage Risk Analysis table, click Medium filter. | Only Medium-risk records appear.
UAT-SMRP-008 Search Material | Verify material search. |  | On Shortage Risk Analysis table: 1. Enter known material number. 2. Enter partial material number. | Matching rows remain visible. Non-matching rows are hidden.
UAT-SMRP-009 Search No Results | Verify material search. |  | On Shortage Risk Analysis table, search invalid material. | No data displayed.
UAT-SMRP-010 Run Shortage Predictor - All Materials | Verify manual worker execution. |  | 1. Click Digital Workers button. 2. Select Shortage Predictor. 3. Keep "Scan All Materials". 4. Click Run Worker. | 1. Execution starts 2. Status displays Running Shortage Predictor - please do not close or cancel this window. 3. Status changes to Completed 4. Success toast appears: "Shortage Predictor executed" 5. User is informed to check email for generated report 6. Email is only sent to the user who executed the manual.
UAT-SMRP-011 Run Shortage Predictor - Selected Materials | Validate required field. |  | 1. Select Scan Specific Materials. 2. Enter any material number. MAT001 MAT002 MAT003 3.Click Run Worker. | 1. Execution starts 2. Status displays Running Shortage Predictor - please do not close or cancel this window. 3. Status changes to Completed 4. Success toast appears: "Shortage Predictor executed" 5. User is informed to check email for generated report
UAT-SRMP-012 View Activity Log | Verify worker execution is logged. |  | 1. Run Shortage Predictor. 2. Return to dashboard. 3.On Digital Worker Activity Log Table. | •Activity Log displays: Notification Sent, RFQ Created, PR Created •Status: Completed •Timestamp updated.
UAT-SMRP-013 Mark Create PR as Done | Verify completion workflow. |  | On Shortage Risk Analysis table: 1.Locate material with action: Create PR 2.Click Done PR. 3.Confirm action. | •Confirmation modal appears. Message: Are you sure you want to mark <MATERIAL> as Done PR? •After confirmation: • Success toast displays. • Action logged. • Page refreshes. • Material no longer displays in shortage list.
UAT-SMRP-014 Mark RFQ as Done | Verify completion workflow. |  | On Shortage Risk Analysis table: 1. Locate Create RFQ item. 2. Click Done RFQ. 3. Confirm. | •Confirmation modal appears. Message: Are you sure you want to mark <MATERIAL> as Done RFQ? •After confirmation: • Success toast displays. • Action logged. • Page refreshes. • Material no longer displays in shortage list.
UAT-SMRP-015 Dashboard Reload After New Prediction | Verify dashboard reflects latest execution. |  | 1. Run Shortage Predictor. 2. Refresh dashboard. | • Latest execution data displayed. • Shortage counts updated. • Activity log updated.
UAT-SMRP-016 Calendar Date Selection | Verify historical dashboard data retrieval. |  | 1. Click the Calendar button. 2. Select a previous date. 3. Observe dashboard reload. | • URL contains selectedDate=yyyy-MM-dd • Dashboard displays data for selected date. • Shortage Risk table reflects historical execution. • Digital Worker Activity Log reflects selected date.
UAT-SMRP-017 Digital Workers Modal | Verify Digital Workers modal launches successfully. |  | 1.Click Digital Workers button. | Modal opens showing: • Shortage Predictor • Inventory Accuracy • Shelf Life Analyzer • Inventory Aging
UAT-SMRP-018 Shortage Predictor Scope Toggle | Verify Scan All Materials / Scan Specific Materials behavior. |  | 1. Click Digital Workers button. 2. Click Shortage Predictor. 3. Select Scan All Materials. 4. Verify textbox is disabled. 5. Select Scan Specific Materials. 6. Verify textbox becomes enabled. | • Scan All Materials → textbox disabled. • Scan Specific Materials → textbox enabled.
UAT-SMRP-019 Empty Material Validation | Validate material entry is required when Scan Specific Materials is selected. |  | 1. Click Digital Workers button. 2. Click Shortage Predictor. 3. Select Scan Specific Materials. 4. Leave textbox empty. 5. Click Run Worker. | Message displayed: Please enter at least one material.
UAT-SMRP-020 Activity Log Sorting | Verify latest activities appear first. |  | 1. Execute Shortage Predictor. 2. Return to dashboard. | • Latest activity appears at top. • Timestamp is updated. • Status displays correctly.
UAT-SMRP-021 Dashboard Refresh By Calendar Date | Verify Refresh button respects selected site/date. |  | 1. Select Site, example PHO or THO. 2. Select historical date. 3. Click Refresh. | • Dashboard reloads. • Site remains selected. • Historical data remains accessible.

## Shortage Predictor UAT Script
System: M2OSS Shortage Prediction Digital Worker (Background Service)
Objective: To verify that the Shortage Prediction Worker Service automatically identifies inventory shortages and provides the correct business recommendations to Planning, Warehouse, and Procurement teams.
Test | Objective | Preconditions | Steps | Expected Result | Actual Results | Status: [Pass/Fail] | Notes | Tester Name | Date Executed
UAT-Shortage_Predictor-001-Verify Scheduled Shortage Analysis | Verify the worker executes automatically according to configured schedule. | • Scheduled execution time has passed. • Worker service is active. | 1. Wait for the scheduled execution time (6:00 AM). 2. Verify that the shortage analysis notification email is received within 5 to 10 minutes before or after the scheduled execution time. 3. Open the S-MRP Dashboard and review the latest shortage analysis results. | • Shortage Predictor worker executes automatically based on the configured schedule. • Shortage analysis email is received within 5 to 10 minutes before or after the scheduled execution time. • Dashboard displays the latest execution results. • Dashboard data is consistent with the information contained in the email report. • Shortage materials are displayed when identified by the analysis. |  | Pass
UAT-Shortage_Predictor-002 Verify PHO/THO Shortage Detection | Verify PHO/THO inventory is evaluated correctly. | Known PHO/THO materials with shortage risk exist. | 1. Wait for worker execution. 2. Open dashboard. 3. Select PHO/THO. | • Shortage materials appear. • Materials with sufficient inventory do not appear. • Displayed risk level is reasonable. |  | Pass
UAT-Shortage_Predictor-003 Verify RFQ Recommendation | Verify worker recommends RFQ when there is no incoming supply. | Business Condition Material has: •Insufficient stock •No Open PO •No valid BPA | 1.Identify known test material. 2.Review shortage recommendation. | Action displayed: Create RFQ |  | Pass
UAT-Shortage_Predictor-004 Verify PR Recommendation | Verify worker recommends PR when BPA exists. | Business Condition Material has: •Valid BPA •No active Open PO •Supply risk detected | Review shortage recommendation for test material. | Action displayed: Create PR |  | Pass
UAT-Shortage_Predictor-005 Verify Expedite Delivery Recommendation | Verify worker identifies late deliveries. | Business Condition Material has: •Existing PO •PO delivery date later than shortage date | Review shortage material. | Action displayed: Expedite delivery |  | Pass
UAT-Shortage_Predictor-006 Verify Expiry-Driven Shortage Detection | Verify worker considers inventory expiration. | Business Condition Material stock exists but expires before consumption. | 1.Wait for scheduled worker execution. 2.Review shortage list. | •Material appears in shortage list despite having stock. •Appropriate replenishment action is recommended. •Materials with expired inventory but insufficient usable supply still appear as shortages. |  | Pass
UAT-Shortage_Predictor-007 Verify Risk Classification | Verify shortage severity is categorized correctly. |  | Review shortage materials. | Materials are classified as: • Critical = DOS ≤ 5 days • High = DOS > 5 and ≤ 7 days • Medium = DOS > 7 days Risk Level displayed in the dashboard matches the material's Days of Supply (DOS).
UAT-Shortage_Predictor-008 Verify Days to Shortage | Verify shortage timing calculations. |  | Review shortage table. | Days to Shortage appears reasonable compared with: •Current Stock •Consumption •Incoming Supply
UAT-Shortage_Predictor-009 Verify Review Planning Profile Recommendation | Verify the worker recommends Planning Profile review when expired inventory exists and no valid planning profile is configured. | Material has: • Inventory quantity exists • Inventory becomes unusable due to expiration • Planning Profile is missing OR • SafetyDays ≤ 0 AND • Usable Stock ≤ 0 after expiry deduction | 1. Await the scheduled execution of the Shortage Predictor at 6:00 AM daily. 2. Review generated shortage output. 3. Locate material with expired stock and missing Planning Profile. | Material appears in shortage output. Status displays: EXPIRED + NO PROFILE Action displays: Review Planning Profile Reason displays: Expired stock with missing planning profile Trigger Date is populated. |  | Pass
UAT-Shortage_Predictor-010 Verify Multiple Expiry Lot Handling | Verify the worker correctly evaluates inventory with multiple lot expiration dates. | Material has: • Multiple inventory lots • Different lot expiration dates • At least one lot expires before projected usage date • At least one lot remains valid | 1. Await the scheduled execution of the Shortage Predictor at 6:00 AM daily. 2. Review shortage result for a material with multiple inventory lots. 3. Compare total inventory quantity versus usable inventory quantity. | Inventory lots expiring before the projected shortage date are excluded from usable supply. Inventory lots with valid expiration dates remain available. Days of Supply (DOS) calculation uses only usable inventory. Shortage recommendation is based on usable inventory rather than total inventory. |  | Pass
UAT-Shortage_Predictor-011 Verify Critical Scenario Detection | Verify the worker identifies materials affected by both inventory expiration and late PO delivery. | Material has: • Inventory expiring before consumption • Existing Open PO • PO Delivery Date later than projected Shortage Date | 1. Await the scheduled execution of the Shortage Predictor at 6:00 AM daily. 2. Review the generated shortage output via email, including the attached Excel report. 3. Locate material meeting the Critical scenario condition. | Material appears in shortage output. Status displays: EXPIRY + PO LATE Action displays: Expedite delivery + Review expired stock Shortage Date is displayed. Delivery Date is displayed. Material is identified as requiring immediate planning action. |  | Pass
UAT-Shortage_Predictor-012 Verify Healthy Stock Exclusion | Verify materials with sufficient inventory coverage are excluded from shortage results. | • Sufficient available inventory • Available supply exceeds shortage threshold • No supply risk detected | 1. Await the scheduled execution of the Shortage Predictor at 6:00 AM daily. 2. Review generated shortage output. 3. Verify materials with healthy inventory levels. | Materials classified as HEALTHY STOCK do not appear in the shortage list. No replenishment recommendation is generated. No RFQ recommendation is generated. No PR recommendation is generated. Only materials requiring action are included in the shortage output. |  | Pass
UAT-Shortage_Predictor-013 Verify Notification Email | Verify that the Shortage Predictor email report is sent to the designated recipients after the analysis is completed. | • Shortage Predictor worker execution has completed successfully. • At least one recipient email address is configured. | 1. Check the Shortage Predictor email report. | • The email report is successfully delivered to the configured recipient(s). • Only the assigned recipient(s) receive the email. |  | Pass
UAT-Shortage_Predictor-014 Verify Shortage Report Attachment | Verify report generation. |  | Open shortage notification email. | Excel attachment exists. Report contains: • Material • Description • Status • StockQty • OpenPoQty • VmiQty • BpaQty • PoPddDate • BpaExpirationDate • ExpiryDate • RfqLeadTime • BpaLeadTime • PrLeadTime • SupplierLeadTime • DOS • Action • TriggerDate • DeliveryDate • ShortageDate |  | Pass

## UAT Coverage
UAT Coverage
S-MRP (Dashboard/Application) | Shortage Predictor (Background Worker)
UAT-SMRP-001 Dashboard Load | 001 Verify Scheduled Shortage Analysis
UAT-SMRP-002 Site Selection | 002 Verify PHO/THO Shortage Detection
UAT-SMRP-003 Manual Refresh | 003 Verify RFQ Recommendation
UAT-SMRP-004 Shortage Risk Summary | 004 Verify PR Recommendation
UAT-SMRP-005 Shortage Filter - Critical | 005 Verify Expedite Delivery Recommendation
UAT-SMRP-006 Shortage Filter - High | 006 Verify Expiry-Driven Shortage Detection
UAT-SMRP-007 Shortage Filter - Medium | 007 Verify Risk Classification
UAT-SMRP-008 Search Material | 008 Verify Days to Shortage
UAT-SMRP-009 Search No Results | 009 Verify Review Planning Profile Recommendation
UAT-SMRP-010 Run Shortage Predictor - All Materials | 010 Verify Multiple Expiry Lot Handling
UAT-SMRP-011 Run Shortage Predictor - Selected Materials | 011 Verify Critical Scenario Detection
UAT-SRMP-012 View Activity Log | 012 Verify Healthy Stock Exclusion
UAT-SMRP-013 Mark Create PR as Done | 013 Verify Notification Email
UAT-SMRP-014 Mark RFQ as Done | 014 Verify Shortage Report Attachment
UAT-SMRP-015 Dashboard Reload After New Prediction
UAT-SMRP-016 Calendar Date Selection
UAT-SMRP-017 Digital Workers Modal
UAT-SMRP-018 Shortage Predictor Scope Toggle
UAT-SMRP-019 Empty Material Validation
UAT-SMRP-020 Activity Log Sorting
UAT-SMRP-021 Dashboard Refresh By Calendar Date

## Flow
SMRP UAT PROCESS FLOW
| ➜ |  | ➜ |  | ➜ | ➜ | ➜ |  | ➜ |  | ➜ | ➜ | ➜ |  | ➜ |  | ➜ | ➜
SHORTAGE PREDICTOR DIGITAL WORKER FLOW
|  | ➜ |  | ➜ |  | ➜ |  | ➜ |  | ➜ |  | ➜ |  | ➜ |  | ➜ |  | ➜
START
Open SMRP Dashboard
Select Site
(PHO/THO)
Load Dashboard Data
Retrieve Latest
Shortage Prediction
Build Risk Analysis
Display Dashboard
Review Risks
Suggest Create PR / RFQ
Confirm Action
Mark Action Done
Refresh Dashboard
END
Digital
Worker runs in the background
Select Shortage
Predictor
Select Plant
Choose Scope
(All/Specific)
Run Worker
Execute
Prediction
Generate Results
Update Dashboard
Update Logs
END